## Slide 1: Property Management System (PMS) Project
Project Initiation Document - Steering Committee Presentation
October 2025
Savills Hong Kong

## Slide 2: Agenda
Executive Summary & Business Case
Current State Challenges
Project Objectives & Scope
Vendor Selection & Recommendation
Financial Analysis & ROI
Implementation Timeline & Approach
Project Team & Resources
Risks & Mitigation
Approval Request & Next Steps

## Slide 3: Executive Summary
Strategic Initiative: Replace 4 legacy systems (Dataswift, e-Procurement, Supplier Mgmt, Sundry Receipt) with integrated SaaS platform
Business Drivers:
End-of-life Dataswift system creating business continuity risk
Manual processes causing inefficiency and errors (80% manual collections)
Lack of integration and data silos limiting visibility and control
Expected Impact:
HKD 11M annual benefit with 2.1-month payback period
DSO reduction from 30 to <25 days (HKD 6.8M cash flow improvement)
70%+ automation of collections activities
40% reduction in AR staffing requirements
Timeline: 7-8 months to Q2 2026 go-live
Investment: HKD 2.1M Year 1, HKD 450K annual recurring

## Slide 4: Current State Challenges
Technology & System Issues:
Dataswift end-of-life with no vendor support
Four disconnected systems creating data silos
No integration with D365, Property Cube, modern payment systems
Operational Inefficiencies:
80% of collections activities are manual
No automated late payment reminders or escalation
Heavy reliance on Excel and paper-based processes
Manual approval routing causing delays
Financial & Compliance Risks:
High DSO (30 days) and bad debt (0.8% of revenue)
Inadequate audit trails and financial controls
PDPO compliance gaps in data privacy
No centralized data repository or single source of truth

## Slide 5: Project Objectives
Management Objectives:
Enhance business resilience through modern, supported technology
Optimize operational efficiency by eliminating manual processes
Improve competitive edge with superior service delivery
Integrate sustainable practices and technologies
Operational Outcomes:
Standardization: Unified workflows, centralized information hub
Risk Mitigation: Enhanced financial controls, automated alerts
Integration: Seamless connectivity with D365, Property Cube, FPS
Automation: End-to-end process automation (billing, collections, procurement)

## Slide 6: Project Scope - In Scope
System Replacement: 4 legacy systems → 1 integrated SaaS platform
21 Core Functional Modules:
Master Data, Billing, Collections, Credit Control with Automated Dunning
Procurement, Vendor Management, Lease Management
Inventory, Fixed Assets, Financial Reporting, Budgeting
Document Management, Workflow, Analytics, Mobile Access
Critical Process Re-engineering:
Late Payment Reminder workflow (D+3 to D+60+ graduated escalation)
Multi-channel communications (Email, SMS, Letter, Phone)
Payment allocation automation (FPS, Autopay, banks, e-wallets)
Key Integrations:
Microsoft Dynamics D365, Property Cube, Active Directory (SSO)
FPS (Faster Payment System), e-Payment gateways, Banks
Email/SMS platforms, Document management

## Slide 7: Project Scope - Out of Scope
Advanced AI functionalities beyond core OCR and automation (Phase 2)
Replacement of Property Cube, D365, or HRIS (integration only)
Hardware provision or network infrastructure upgrades (SaaS platform)
Business processes not in User Requirement Checklist
Extensive custom development beyond configuration and integration

## Slide 8: Vendor Evaluation Process
Phase 1 (2023): Initial Market Scan
6 vendors evaluated → 3 shortlisted
Phase 2 (Early 2025): Detailed Evaluation
3 vendors submitted proposals and demos
Evaluated against 500+ requirements across 21 modules
Reference checks with HK property management clients
Result: 2 finalists (MRI Software, Kingdee)
Phase 3 (Mid 2025): Deep Dive & Workshops
Multi-day workshops (July-August 2025)
Process walkthroughs, integration POCs, site visits
Detailed cost analysis and implementation approach
Final recommendation prepared (October 2025)

## Slide 9: Vendor Comparison - MRI vs Kingdee
Criteria | MRI Software | Kingdee
Functional Fit | 95%+ requirements met | 95%+ requirements met
HK Market Presence | Excellent - Multiple tier-1 clients | Very Good - Growing client base
Technology Platform | Modern SaaS, Cloud-native | Modern SaaS, Cloud-native
Integration Capability | Pre-built D365, FPS connectors | Good - Standard APIs
Collections Module | Excellent - Proven dunning | Good - Standard features
Implementation | Proven HK methodology | Structured approach
Customer References | Excellent feedback | Good feedback
3-Year TCO | HKD 3.64M | HKD 3.14M (16% lower)

## Slide 10: Vendor Recommendation: MRI Software
Recommendation: MRI Software (subject to final negotiation)
Key Justification:
Strongest HK market track record with tier-1 property managers
Pre-built integrations (D365, FPS, banks) reduce risk and development
Superior collections module aligns with Late Payment Reminder design
Excellent customer references - high satisfaction scores
Proven implementation methodology reduces delivery risk
Cost Premium Analysis:
16% higher TCO (HKD 500K over 3 years)
Offset by reduced integration risk, faster time-to-value, lower operational risk
Higher probability of achieving targeted benefits
Contingency: Kingdee as strong backup if negotiations fail

## Slide 11: Financial Analysis - Year 1 Investment
Category | Amount (HKD) | Description
System Configuration | 800,000 | Setup and configuration
Integration Development | 500,000 | FPS, D365, Property Cube, payments
Templates & Process Design | 100,000 | Bilingual templates, workflows
Data Migration | 200,000 | Extract, transform, load from legacy
Training & Change Mgmt | 200,000 | Materials, workshops, support
SaaS Licensing (pro-rated) | 300,000 | Platform licenses, communications
Total Year 1 | 2,100,000 | 
Annual Recurring (Year 2+) | 450,000 | Licenses and support

## Slide 12: Financial Analysis - Annual Benefits & ROI
Metric | Value | Notes
Cash Flow Improvement | HKD 6.8M | DSO: 30→25 days (5-day improvement)
Bad Debt Reduction | HKD 1.5M | 0.8% → 0.5% (0.3% improvement)
AR Staffing Savings | HKD 2.0M | 40% reduction (10→6 FTE)
Late Fee Collection | HKD 0.8M | Collection rate: 60%→85%
Legal Fee Reduction | HKD 0.2M | Fewer escalations (40% reduction)
Process Efficiency | HKD 0.7M | Procurement, reporting automation
Total Annual Benefit | HKD 12.0M | 
Payback Period | 2.1 months | Year 1 investment / annual benefit
3-Year NPV @ 8% | HKD 29M | Substantial value creation
IRR | >400% | Exceptional return on investment

## Slide 13: Implementation Timeline - 7-8 Months
Phase 1: Project Initiation (3-4 weeks) - Kickoff, planning, mobilization
Phase 2: Requirements & Design (6 weeks) - Workshops, process design, integration specs
Phase 3: System Build (6 weeks) - Configuration, integration dev, template creation
Phase 4: Data Migration (4 weeks, parallel) - Extract, cleanse, transform, test
Phase 5: Testing (6 weeks) - SIT, UAT, integration, performance testing
Phase 6: Training (4 weeks, parallel) - Materials, train-the-trainer, end-user training
Phase 7: Go-Live Prep (2 weeks) - Final migration, cutover planning, readiness review
Phase 8: Go-Live & Hypercare (4 weeks) - Production cutover, stabilization, support
Target Go-Live: Q2 2026 (June 2026)

## Slide 14: Key Project Milestones
Milestone | Week from Approval | Success Criteria
Project Kickoff | 1 | Team mobilized, vendor contract signed
Requirements Sign-off | 10 | All requirements documented and approved
Design Sign-off | 12 | Process flows, configs, integrations approved
System Build Complete | 18 | All modules configured, integrations functional
UAT Complete | 24 | All test cases passed, UAT sign-off
Training Complete | 26 | All users trained, materials finalized
Go-Live | 28 | Production system live, support activated
Hypercare Complete | 32 | System stable, BAU support transitioned
Post-Implementation Review | 34 | Benefits tracking, lessons learned

## Slide 15: Project Approach & Methodology
Methodology: Hybrid Waterfall (governance) + Agile (flexibility)
Governance Structure:
Steering Committee (monthly) - CFO, Head of Ops, IT Director, PM Head
Project Management Office - PM, BA, Change Manager
Core Team (30-50% during peak) - Finance, Operations, IT, Procurement leads
Extended Team / SMEs - Collections, billing, procurement specialists
Quality Assurance:
Peer review of design documents before approval
Configuration checkpoints at 25%, 50%, 75%, 100%
Independent QA before UAT; 80% test coverage minimum
Data reconciliation after every migration test
Change Management:
Stakeholder engagement plan, super user network
Role-based training, readiness assessments, post-go-live support

## Slide 16: Project Team & Resource Requirements
Steering Committee: Overall governance and major decisions
CFO (Sponsor), Head of Operations, IT Director, Head of PM
Core Project Team (Key Roles & Effort):
Project Manager (800-1,000 hrs) - Day-to-day management, vendor coordination
Business Analyst (600-800 hrs) - Requirements, process design, UAT
IT Lead (400-600 hrs) - Integrations, infrastructure, security
Finance Lead (400-600 hrs) - Billing/collection requirements, controls, UAT
Operations Lead (300-500 hrs) - Property mgmt workflows, lease mgmt, UAT
Data Lead (300-400 hrs) - Data mapping, migration, quality validation
Change Manager (300-400 hrs) - Communications, training, adoption
Extended Team: SMEs for billing, collections, procurement (2,000-3,000 hrs cumulative)
Vendor Team: Full-time PM, architects, consultants during implementation

## Slide 17: Top Project Risks & Mitigation
Risk | Impact | Mitigation Strategy
Stakeholder availability | High | Secure commitment upfront; backfill BAU; protected time
Data quality issues | Medium | Early data profiling; dedicated cleansing; buffer time
Integration complexity (D365) | High | Early POC; MRI pre-built connector; IT Lead engaged
Scope creep | Medium | Clear baseline; change control; Steering approval
UAT defects exceed expected | High | Thorough SIT before UAT; QA; vendor rapid fixes
User resistance | High | Strong change mgmt; early engagement; training
Go-live cutover delays | High | Detailed plan; dry runs; low-volume period
PDPO compliance gaps | High | Early legal review; consent mgmt; audit trail
Budget overrun | Medium | 10% contingency; change control; vendor fixed price
Dataswift failure before go-live | Critical | Accelerate timeline; manual workarounds; vendor support

## Slide 18: Critical Dependencies
Vendor & Contract (Week 1):
Vendor contract signed and resources allocated
Project team released from BAU duties
Integration Dependencies (Weeks 8-12):
D365 test environment and API access
Property Cube integration specs and API
Active Directory SSO configuration
FPS integration credentials from banks
Email/SMS gateway setup and testing
Compliance & Security (Weeks 4-6):
IT Security approval on vendor security assessment
Legal sign-off on PDPO compliance and Data Processing Agreement
Go-Live Critical Path (Weeks 24-26):
Production cutover window approved by business
Network bandwidth and infrastructure confirmed
Hypercare support model confirmed (vendor + internal)

## Slide 19: Non-Financial Benefits
Business Continuity: Eliminate Dataswift end-of-life risk
Risk Mitigation: Enhanced controls, audit trails, PDPO compliance
Tenant Satisfaction: Improved communications, payment options, service
Staff Productivity: Eliminate manual data entry and reconciliation
Decision Making: Real-time dashboards, analytics, reporting
Scalability: Platform supports growth without proportional cost increase
Competitive Advantage: Modern system positions Savills as HK market leader
Data Quality: Single source of truth eliminates inconsistencies
Environmental: Reduced paper through digital workflows and e-communications

## Slide 20: Approval Request
The Project Steering Committee is requested to approve:
1. Project Scope: Replace 4 legacy systems with integrated PMS
2. Budget: HKD 2.1M Year 1 investment + HKD 450K annual recurring
3. Vendor Selection: Proceed with MRI Software (subject to final negotiation)
4. Resource Commitment: Allocate business resources per Section 6 estimates
5. Timeline: Target go-live Q2 2026 (June 2026)
Immediate Next Actions (upon approval):
Finalize vendor contract and mobilize resources (Week 1)
Establish project governance and PMO (Week 1)
Initiate integration discussions (D365, Property Cube, FPS) (Week 2)
Conduct IT security and PDPO compliance reviews (Weeks 2-6)
Project kickoff and requirements workshops (Week 2+)

## Slide 21: Why This Project Must Proceed
Business Imperatives:
Dataswift end-of-life creating critical business continuity risk
Current manual processes unsustainable as business grows
Competitive disadvantage vs. peers with modern systems
Financial Imperative:
Exceptional ROI (>400% IRR, 2.1-month payback)
HKD 29M in 3-year value creation
HKD 6.8M annual working capital improvement
Operational Imperative:
70%+ reduction in manual effort through automation
40% staffing efficiency gain in AR operations
Enhanced financial controls and PDPO compliance
Strategic Imperative:
Foundation for future digital transformation
Positions Savills as technology leader in HK property management
Enables data-driven decision making and continuous improvement

## Slide 22: Questions & Discussion
Thank you for your consideration.
We are ready to answer any questions and
discuss next steps.
Contact:
Project Team
Savills Hong Kong
October 2025